## Slide 1
PROJECT DEVELOPMENT PACKAGE
Padang Besar
Cross-Border Logistics Platform
Perlis, Malaysia · Malaysia–Thailand Border Corridor
Prepared for discussions with: Government agencies · Investors · Shandong Hi-Speed Group · EPC contractors · Technology partners · Banks
Draft for discussion · July 2026 · Prepared by the Prospek Cerah project development team
This document asserts no ownership, concession, operating rights or licences. Items not publicly verified are marked “Pending confirmation from project owner.”

## Slide 2
Padang Besar Cross-Border Logistics Platform · Project Development Package · Draft for discussion — not an offer or representation of rights
2
BASIS OF PREPARATION
How this document was built — and what it does not claim
RECOMMENDATION
Prepared by a multi-disciplinary development team covering project development, PPP/infrastructure, inland-port logistics, EPC, digitalisation, financial modelling, investment banking, risk, government relations and presentation design. Each specialist's output was cross-reviewed by the others before inclusion.
Research base: publicly available sources only, verified as of 26 July 2026. Every factual statement in Section 2 carries a reference [R#], consolidated in the References appendix.
Where public sources conflict (e.g., Perlis Inland Port capacity and cost figures), the conflict is disclosed rather than resolved by assumption.
No site visits, data-room access or owner interviews have occurred. Nothing here should be read as confirmation of land, rights, mandates or approvals.
All business models, work packages, structures and financial frameworks are proposals for negotiation — deliberately built so they can be validated or discarded item-by-item in due diligence.
DOCUMENT DISCIPLINE
Never fabricate facts
Separate fact tiers on every page
Disclose source conflicts
State what is unverified
No numbers without evidence

## Slide 3
Padang Besar Cross-Border Logistics Platform · Project Development Package · Draft for discussion — not an offer or representation of rights
3
READING GUIDE
Four information tiers — kept separate throughout
PUBLICLY VERIFIED
Facts supported by cited public sources (media, government, corporate disclosures). Each carries a reference [R#].
PENDING OWNER CONFIRMATION
Anything about this project's land, rights, mandates, agreements or status. Not asserted anywhere in this package.
PROPOSED
Business model, work packages, structures and strategies designed by the team — for negotiation, not statements of fact.
RECOMMENDATION
The team's professional judgment on sequencing, positioning and process — clearly separated from facts.

## Slide 4
Padang Besar Cross-Border Logistics Platform · Project Development Package · Draft for discussion — not an offer or representation of rights
4
CONTENTS
Fifteen sections, one investment-grade narrative
01
Executive Summary
02
Public Research (referenced)
03
Current Ecosystem
04
Project Opportunities
05
EPC Work Packages WP01–WP20
06
Digitalisation Strategy
07
Prospek Cerah Business Model
08
Shandong Hi-Speed Role
09
Investment Model
10
Financial Model Framework
11
Due Diligence Checklist
12
Questions for Project Owner
13
Consortium Structure
14
Risk Register
15
Roadmap & Next Steps
+ Appendix: visual asset recommendations · assumptions register · consolidated references

## Slide 5
Padang Besar Cross-Border Logistics Platform · Project Development Package · Draft for discussion — not an offer or representation of rights
5
01
Executive Summary
Why Padang Besar, why Malaysia, why border logistics — and the one strategic question that must be answered before any capital moves.
Why Padang Besar
Why Malaysia
Why border logistics
Opportunities & challenges
The honest bottom line

## Slide 6
Padang Besar Cross-Border Logistics Platform · Project Development Package · Draft for discussion — not an offer or representation of rights
6
SECTION 1 · EXECUTIVE SUMMARY
Why Padang Besar: the corridor is real, growing and under-built
PUBLICLY VERIFIED
+25.9%
Padang Besar (Thai) checkpoint trade growth 2024 — 102.3bn baht, 3rd in Thailand for transshipment value [R48]
Only
direct Malaysia–Thailand rail link — juxtaposed customs inside the station [R2, R3]
~80%
utilisation of the 150,000 TEU legacy terminal before operations migrated [R15]
16 hrs
road border window (06:00–22:00) — a solvable structural constraint [R4]
Through this single crossing already run: the electrified KTMB double-track corridor, the CMA CGM/Infinity Penang landbridge block trains, the ASEAN Express to Chongqing, and daily freight into the new Perlis Inland Port. The infrastructure conversation at this border has already started — the question is who builds its next layer. [R10–R13]

## Slide 7
Padang Besar Cross-Border Logistics Platform · Project Development Package · Draft for discussion — not an offer or representation of rights
7
SECTION 1 · EXECUTIVE SUMMARY
Why Malaysia: a policy machine is already funding this corridor
PUBLICLY VERIFIED
US$30bn
official Malaysia–Thailand trade target for 2027, with a joint trade-facilitation task force [R46]
PIKAS 2030
national PPP master plan: RM78bn private investment target, competitive RFP model [R61]
NCIA / NCER
statutory development authority for Perlis with logistics as a mandated sector [R56]
~RM400m
government external works already delivered at this border (bonded road, rail spur, flyover) [R23, R36]
RM374m
Bank Pembangunan financing approved for Perlis Inland Port — lender precedent at this exact location [R25]
Border Economic Zone
announced by both Prime Ministers, July 2026 — spanning the northern border states [R60]
Malaysia pairs this policy stack with a common-law system, deep sukuk/project-finance markets, and institutional lenders (BPMB, AIIB partnerships with Maybank/CIMB/AmBank) active in exactly this asset class. [R80]

## Slide 8
Padang Besar Cross-Border Logistics Platform · Project Development Package · Draft for discussion — not an offer or representation of rights
8
SECTION 1 · EXECUTIVE SUMMARY
Why border logistics: chokepoint economics with a rail growth option
VERIFIED FACTS + PROPOSAL
Land-border trade is ~40% of US$25bn bilateral trade (2024) — and this checkpoint grew +25.9% while the total grew single digits. [R47, R48]
Border logistics is a chokepoint business: where two customs regimes, two rail operators and two road networks meet, every improvement in flow is monetisable — handling, storage, marshalling, data.
Cross-border flows are the least commoditised, highest-friction segment of ASEAN logistics — friction is the revenue pool.
The China–ASEAN rail narrative (ASEAN Express since 2024; Kunming–Singapore corridor phases to 2031) adds a structural growth option on top of the bilateral base. [R12, R54]
~70% of southern Thailand's export cargo already transships through Penang — the landbridge through Padang Besar is its land leg. [R51]
WHY NOW
PIP operating + FCZ live (May 2026): ecosystem momentum
SRT Hat Yai–Padang Besar double-tracking at bid stage [R35]
Border Economic Zone incentives being defined now
13MP road-to-rail push; KTMB volumes +23.5% YoY [R33, R34]
Positioning windows close once corridors consolidate

## Slide 9
Padang Besar Cross-Border Logistics Platform · Project Development Package · Draft for discussion — not an offer or representation of rights
9
SECTION 1 · EXECUTIVE SUMMARY
The honest bottom line — and the strategic question
RECOMMENDATION
WHAT IS VERIFIED
The corridor: trade volumes, growth, rail services, policy support
The precedents: PIP financing, Thanaleng model, Shandong Hi-Speed active in Malaysia
The constraints: border hours, Thai single-track, competition
WHAT IS NOT VERIFIED
This project's land, rights, mandate and approvals
Its relationship to the operating Perlis Inland Port
Any commitment by Shandong Hi-Speed, government or investors
THE STRATEGIC QUESTION
Perlis Inland Port is operating in the same town — state-backed, KTMB-run, royally launched. This project must define itself as integration, complement, or competitor to PIP before approaching any investor. This package is built to force that answer early (Sections 11–12), then convert the verified corridor thesis into an investable transaction (Sections 13–15).

## Slide 10
Padang Besar Cross-Border Logistics Platform · Project Development Package · Draft for discussion — not an offer or representation of rights
10
02
Public Research
Only publicly verifiable information, every statement referenced. Conflicting sources are disclosed; unverifiable items are quarantined.
Border & rail anatomy
Perlis Inland Port
Trade statistics
Policy & stakeholders
What we could not verify

## Slide 11
Padang Besar Cross-Border Logistics Platform · Project Development Package · Draft for discussion — not an offer or representation of rights
11
SECTION 2 · PUBLIC RESEARCH
The border system: one town, two regimes, three channels
PUBLICLY VERIFIED
Channel | Verified facts | Refs
Rail | Malaysia's only direct rail link with Thailand. Station (1918) hosts juxtaposed MY+TH border controls. KTMB electrified double-track metre-gauge line meets SRT Southern Line. No gauge break — both networks are metre gauge; the standard-gauge break for China traffic is at Thanaleng, Laos. | R2, R3, R9, R30
Road | ICQS complex handles passenger + cargo vehicles; hours ~06:00–22:00 (not 24h). Federal Route 7 starts at the border; FT79 links south; expressway via Changlun. The busier road crossing is Bukit Kayu Hitam–Sadao, 45 km east — new link road opened July 2026. | R4, R6–R8, R42, R43
Customs | JKDM/RMCD administers the land entry point. National digital rails: uCustoms/SMK; ASEAN Single Window live for e-Form D across all 10 member states. ACTS transit system piloted by MY–SG–TH. Single-stop inspection studied (CAREC), implementation unverified. | R18, R21, R44, R45
Detail slide 3.2 maps these channels as a flow diagram.

## Slide 12
Padang Besar Cross-Border Logistics Platform · Project Development Package · Draft for discussion — not an offer or representation of rights
12
SECTION 2 · PUBLIC RESEARCH
Rail cargo: four services already run through this crossing
PUBLICLY VERIFIED
KTMB Kargo landbridge
Container services linking Penang Port, Port Klang and Padang Besar; ~4-day transit concept. [R10]
Penang block train (2022)
CMA CGM / Infinity Penang–Padang Besar service; corridor reported up to 7,500 TEU/month. [R11]
ASEAN Express (2024)
KL (Kontena Nasional ICD) → Padang Besar → Lat Krabang → Thanaleng → Chongqing. ~9–14 days vs 14–21 by sea. [R12, R31]
STC Perai–PIP (2025)
Daily freight into Perlis Inland Port; first train 80 TEU on 1 Dec 2025. [R13]
Capacity outlook
13MP-era plans: Padang Besar Depot upgrade, road-to-rail shift, North Butterworth terminal upgrade [R33]; KTMB rail volumes +23.5% YoY Jan 2026 [R34]
Thai side: SRT double-tracking Hat Yai–Padang Besar (45 km, ~7.77bn baht) slated for bidding within 2026 [R35]

## Slide 13
Padang Besar Cross-Border Logistics Platform · Project Development Package · Draft for discussion — not an offer or representation of rights
13
SECTION 2 · PUBLIC RESEARCH
Perlis Inland Port: the operating incumbent next door
PUBLICLY VERIFIED
2022
Construction launch; NCIA external works (bonded road, rail spur, flyover)
Mar–Apr 2025
KTMB O&M agreement; Maersk MOC; Kalmar equipment
1 Dec 2025
First commercial freight train (80 TEU, Perai–PIP)
12 Apr 2026
Operations migrate from legacy TKPB terminal
30 May 2026
Raja of Perlis launches Free Commercial Zone
500 acres
site with bonded road + rail siding [R17]
600,000
TEU/yr stated current capability [R17]
RM374m
BPMB financing approved [R25]
80 : 20
Mutiara Infra : Perlis MB Inc ownership of Mutiara Perlis [R14]
Disclosed source conflicts: total cost reported between RM327m and RM492m across outlets; ultimate capacity reported as both 1M and 2M TEU/yr. Figures used here are the best-attested official statements. [R17, R26, R27, R37, R38]

## Slide 14
Padang Besar Cross-Border Logistics Platform · Project Development Package · Draft for discussion — not an offer or representation of rights
14
SECTION 2 · PUBLIC RESEARCH
Malaysia–Thailand trade: the demand base is verified
PUBLICLY VERIFIED
US$25.06bn
bilateral trade 2024; ~40% via land borders [R47]
US$30bn
official 2027 target (3rd Joint Trade Committee) [R46]
102.3bn baht
Padang Besar checkpoint 2024, +25.9% YoY [R48]
315.1bn baht
Thai–Malaysia border trade 2025 — Thailand's largest border partner [R49]
What moves across this border
Exports through Sadao/Padang Besar led by hard disk drives and processed wood; rubber (TSNR) via Songkhla checkpoints +39.3% [R48]
F&B reported as the largest cross-border category, followed by E&E (single source) [R50]
Sadao handles ~2× Padang Besar's trade value — but Padang Besar is growing far faster and owns the rail channel [R48]
~70% of southern Thailand's export cargo transships via Penang — the corridor this platform would serve [R51]

## Slide 15
Padang Besar Cross-Border Logistics Platform · Project Development Package · Draft for discussion — not an offer or representation of rights
15
SECTION 2 · PUBLIC RESEARCH
Government initiatives: federal, state and bilateral layers
PUBLICLY VERIFIED
Layer | Initiative | Relevance | Refs
Bilateral | US$30bn 2027 target + task force; Border Economic Zone announced Jul 2026; new BKH–Sadao road opened | Political momentum for border trade infrastructure | R46, R60, R42
Federal | PIKAS 2030 PPP master plan; National Transport Policy 2019–30; 13MP road-to-rail + Padang Besar Depot upgrade; NIMP 2030 (logistics as enabler) | Defines the PPP route (UKAS RFP), rail investment pipeline | R61, R58, R33, R59
Regional | NCIA (Act 687) mandate for NCER; Chuping Valley Industrial Area (2,482 acres, green/halal); IMT-GT corridor | The statutory sponsor that already co-funded PIP external works | R56, R57, R53
State | Perlis investment drive (MIDA Invest Series 2025); Padang Besar designated growth area; largest-ever state budget 2026 | State government actively courting logistics investment | R39, R64, R65
Ownership rules | ≥51% Malaysian ownership floor for port/strategic concessions (reaffirmed Jul 2026); Bumiputera equity conditions in logistics licensing | Hard constraint on consortium design (Section 13) | R62, R63

## Slide 16
Padang Besar Cross-Border Logistics Platform · Project Development Package · Draft for discussion — not an offer or representation of rights
16
SECTION 2 · PUBLIC RESEARCH
The Thai side: capacity is coming toward this border
PUBLICLY VERIFIED
SRT southern double-tracking package includes Hat Yai–Padang Besar (45 km, ~7.77bn baht) — explicitly framed as strategic for the Malaysia corridor; bidding targeted within 2026. [R35]
Thai CIQ upgrade plans reported at Padang Besar (single source — scope/budget unpublished). [R20]
New Sadao CIQ–Bukit Kayu Hitam road opened 10 July 2026 (11 vehicle + 14 immigration lanes/side, dual X-ray cargo terminal) — strengthens the competing road corridor. [R42]
Songkhla is southern Thailand's logistics province: rubber, wood, seafood export base; Padang Besar (Thai) station is the Southern Line freight terminus. [R48]
Thai Land Bridge (Chumphon–Ranong) remains in study flux — fresh environmental studies ordered June 2026; a long-run variable, not a near-term constraint. [R55]
READ-THROUGH
Rail capacity into Padang Besar is being doubled from the Thai side while road capacity consolidates at Sadao–BKH. A rail-centred platform at Padang Besar aligns with where both governments are putting steel.

## Slide 17
Padang Besar Cross-Border Logistics Platform · Project Development Package · Draft for discussion — not an offer or representation of rights
17
SECTION 2 · PUBLIC RESEARCH
Stakeholder map: who already acts in this corridor
PUBLICLY VERIFIED
Cluster | Stakeholders (published roles) | Refs
Federal | MOT (rail/logistics policy; PIP champion) · MITI/MIDA (trade target, promotion) · JKDM Customs · UKAS (PPP gatekeeper) · Railway Assets Corporation | R33, R46, R61
Regional/State | NCIA (external infra funder, CVIA developer) · Perlis state govt & MB Inc (20% of Mutiara Perlis) · Padang Besar growth-area designation | R14, R23, R56, R65
Rail & ports | KTMB (ASEAN Express, PIP O&M, TKPB) · SRT (Southern Line, double-tracking) · Penang Port (70% of southern-Thai transshipment) · Kontena Nasional (ASEAN Express origin ICD) | R12, R16, R35, R51
Corporate | Mutiara Perlis / Perlis Inland Port Sdn Bhd · Maersk (MOC) · CMA CGM/Infinity (block train) · Citaglobal, Berjaya Property (equity moves) · Kalmar (equipment) | R11, R22, R39, R41
Thai side | Thai Customs (Padang Besar & Sadao houses) · SRT · Songkhla province · Thai MOT/OTP | R35, R42, R48

## Slide 18
Padang Besar Cross-Border Logistics Platform · Project Development Package · Draft for discussion — not an offer or representation of rights
18
SECTION 2 · PUBLIC RESEARCH
What we could not verify — quarantined from all argumentation
PENDING OWNER CONFIRMATION
Ultimate PIP capacity (1M vs 2M TEU/yr) and total PIP cost (RM327m–RM492m across outlets) — conflicting public figures
Malaysian checkpoint-level trade statistics (JKDM does not publish; Thai customs data used instead)
Free Commercial Zone gazettement instrument; bonded warehouse licences at PIP
uCustoms operational status at Padang Besar specifically; single-stop inspection implementation
Any route designated “R15” serving Padang Besar (referenced in early briefs — no such designation found)
Current Shandong Hi-Speed parent credit rating; Chinese trade-press claims of “>RMB 60bn Malaysia orders”
Any MMC Corporation involvement in PIP; any SDHS/CSI mandate in Perlis
Rail share of bilateral trade; ASEAN Express cumulative volumes
Border Economic Zone boundaries and incentives (announced July 2026; details unpublished)
Rule applied: anything on this list is excluded from the business case and routed to due diligence (Section 11) or owner questions (Section 12).

## Slide 19
Padang Besar Cross-Border Logistics Platform · Project Development Package · Draft for discussion — not an offer or representation of rights
19
03
Current Ecosystem
How cargo actually moves through Padang Besar today — road, rail, warehouse, container, cold chain, border and customs.
Corridor flow map
Border process flows
Facility inventory
Ecosystem gaps

## Slide 20
Padang Besar Cross-Border Logistics Platform · Project Development Package · Draft for discussion — not an offer or representation of rights
20
SECTION 3 · CURRENT ECOSYSTEM
Corridor flow: how the pieces connect
PUBLICLY VERIFIED
THAILAND · Songkhla
Hat Yai rail hub
SRT Southern Line (metre gauge)
Thai roads / Sadao
trucking to border
PADANG BESAR
Station (juxtaposed CIQ) + road ICQS 06:00–22:00
MALAYSIA · Perlis and beyond
Perlis Inland Port
500-acre FCZ, bonded road, rail siding
KTMB West Coast Line
electrified double track, metre gauge
Penang Port (NBCT)
landbridge sea gateway — 70% of southern-Thai transshipment
Klang Valley / Port Klang
national market + ASEAN Express origin
China corridor
via Lat Krabang → Thanaleng (gauge break) → Chongqing
Key structural facts
No gauge break at this border (both metre gauge) — rail interchange here is commercial, not technical [R9, R30]
Road cargo constrained by the 16-hour border window; heavy road flows consolidating at Bukit Kayu Hitam–Sadao [R4, R42]

## Slide 21
Padang Besar Cross-Border Logistics Platform · Project Development Package · Draft for discussion — not an offer or representation of rights
21
SECTION 3 · CURRENT ECOSYSTEM
Border process: rail vs road today
PUBLICLY VERIFIED
RAIL CARGO (juxtaposed controls)
Load at origin ICD
KL / Perai / Lat Krabang
Line-haul
KTMB or SRT metre gauge
Padang Besar station
MY + TH clearance co-located
Onward line-haul
no transshipment needed
ROAD CARGO (sequential controls, 06:00–22:00)
Queue at approach
no managed marshalling documented
Exit CIQ
origin-side customs & immigration
Entry ICQS/CIQ
destination-side inspection
Onward haulage
FT7/FT79 → expressway via Changlun
The friction points are visible: unmanaged truck queues against a hard 22:00 cutoff, paper-heavy road clearance, and no published integrated visibility from booking to release. Rail avoids most of this — which is why the corridor's growth is running through it. (Team interpretation based on referenced facts.)

## Slide 22
Padang Besar Cross-Border Logistics Platform · Project Development Package · Draft for discussion — not an offer or representation of rights
22
SECTION 3 · CURRENT ECOSYSTEM
Facility inventory: what exists at the border today
PUBLICLY VERIFIED
Element | Current state (published) | Refs
Container terminal | Legacy TKPB: 150,000 TEU/yr, ~80% utilised before migration; operations moved to PIP 12 Apr 2026 | R15, R16
Inland port / FCZ | PIP: 500 acres, 600,000 TEU/yr capability, bonded road, rail siding, FCZ launched 30 May 2026 | R17
Warehousing | PIP warehousing targets halal, automotive, rubber; no other large modern stock documented at the border | R14
Cold chain | No large-scale multi-user cold-chain facility documented in public sources — apparent white space (interpretation) | —
Truck facilities | No managed marshalling/booking system documented; border hours 06:00–22:00 | R4
Customs facilities | ICQS complex (road) + juxtaposed controls (rail); Thai CIQ upgrade plans reported (single source) | R3, R20
Handling equipment | PIP: RM17m Kalmar order (15 units) via Mach 1, May 2025 | R36

## Slide 23
Padang Besar Cross-Border Logistics Platform · Project Development Package · Draft for discussion — not an offer or representation of rights
23
SECTION 3 · CURRENT ECOSYSTEM
Ecosystem gaps: five white spaces (team interpretation)
RECOMMENDATION
1
Cold chain at scale
Perishables flow both ways (Thai fruit/seafood south, Malaysian halal north) with no documented multi-user cold facility at the border.
2
Truck marshalling
A hard 22:00 cutoff with unmanaged queues = monetisable slot booking, secure parking and call-up services.
3
Digital corridor visibility
No published integrated system links booking → gate → customs status → release across the crossing.
4
Free-zone VAS
Labelling, kitting, halal certification support and light processing inside zone conditions — early-stage at PIP.
5
24-hour operations
A bilateral policy matter, repeatedly raised, unresolved — the single biggest unlock, outside private control.
These five gaps are the demand hypotheses the feasibility study must test — they are interpretations, not established markets.

## Slide 24
Padang Besar Cross-Border Logistics Platform · Project Development Package · Draft for discussion — not an offer or representation of rights
24
04
Project Opportunities
The opportunity map across the platform lifecycle — construction, operations, commercial, asset management, expansion, digital.
Construction scope
Operations & commercial
Asset management
Expansion & digital

## Slide 25
Padang Besar Cross-Border Logistics Platform · Project Development Package · Draft for discussion — not an offer or representation of rights
25
SECTION 4 · PROJECT OPPORTUNITIES
Build & operate: the physical opportunity set
PROPOSED
Construction (◆ = needs land/rights, ● = needs govt/agency agreement) | Operations
Site development & flood-resilient earthworks ◆ | Terminal operations: rail yard + container yard (self-perform or operator partner)
Warehouses: ambient, bonded, cold chain — smart-warehouse spec ◆ | Warehouse operations: 3PL contracts, bonded ops, cold-chain management
Rail sidings & terminal trackworks (KTMB agreement) ◆● | Truck terminal: marshalling, booking slots, secure overnight parking
Internal roads, truck marshalling infrastructure ◆ | Facility management, security, equipment maintenance & rental
Utilities: substations, water, fire, solar PV, standby power ◆ | Reefer pre-trip inspection, container repair & washing
Buildings: admin, commercial, customs/agency facilities ◆● | Border-services support offered to agencies (inspection support) ●
Digital infrastructure built with civil works, not retrofitted ◆ | Energy services: solar PPA, energy-as-a-service for cold tenants
Precedent: the SDHS–PTT Synergy smart-warehousing framework (Sep 2025) shows the build model is already active in Malaysia. [R72, R73]

## Slide 26
Padang Besar Cross-Border Logistics Platform · Project Development Package · Draft for discussion — not an offer or representation of rights
26
SECTION 4 · PROJECT OPPORTUNITIES
Commercial, asset management and digital layers
PROPOSED
COMMERCIAL
Anchor leasing: 3PLs, forwarders, Thai & Malaysian shippers, e-commerce
Free-zone VAS: labelling, kitting, halal support, light assembly ●
Trade services cluster: brokers, banks, insurers, surveyors as tenants
Fuel, retail, F&B concessions serving driver traffic
ASSET MANAGEMENT
ISO 55000 regime as a paid service to the SPV and zone tenants
Capex renewal programme management over a 30+ year life
Energy management and solar PPA structures
Digital-twin-driven lifecycle optimisation (Section 6)
DIGITAL
Corridor visibility platform: booking → gate → customs → delivery
Data products for shippers, forwarders and agencies
Smart-warehouse services on SDHS-ecosystem automation
Command-centre services to tenants and, potentially, agencies ●
● = requires government/agency agreement — routed to Section 12 owner questions and Phase 1–2 engagement.

## Slide 27
Padang Besar Cross-Border Logistics Platform · Project Development Package · Draft for discussion — not an offer or representation of rights
27
SECTION 4 · PROJECT OPPORTUNITIES
Expansion options: what Phase 2+ can become
PROPOSED
E-commerce fulfilment campus
Riding cross-border e-commerce growth on the rail corridor
Halal logistics hub
Aligned with Chuping Valley Industrial Area's halal-industry positioning ● [R57]
Cold-chain corridor scaling
Growing with Thai perishables and Malaysian halal exports
Standard-gauge readiness
Passive provision if Pan-Asian rail plans ever extend south ●
Model replication
Apply the platform + digital playbook at other crossings (Rantau Panjang, Bukit Kayu Hitam)
Border Economic Zone play
Participate once incentives are gazetted (announced Jul 2026) ● [R60]
All expansion options are design-stage provisions only — safeguarded land and corridors (WP20), not committed scope.

## Slide 28
Padang Besar Cross-Border Logistics Platform · Project Development Package · Draft for discussion — not an offer or representation of rights
28
05
EPC Work Packages
Twenty packages structured for consortium scope allocation, staged financing and early-revenue sequencing. Scope and siting pending owner confirmation.
WP01–04 Enabling
WP05–10 Core logistics
WP11–14 Buildings & border
WP15–17 Digital
WP18–20 Readiness & expansion

## Slide 29
Padang Besar Cross-Border Logistics Platform · Project Development Package · Draft for discussion — not an offer or representation of rights
29
SECTION 5 · WORK PACKAGES
WP01–WP10: enabling works and core logistics infrastructure
PROPOSED
WP | Package | Scope highlights
WP01 | Site investigation & surveys | Topo/geotech/hydrology, utilities, boundary, environmental & social baseline, border traffic counts
WP02 | Enabling works & earthworks | Clearance, cut-and-fill, ground improvement, platform formation, construction drainage
WP03 | Utilities & services | Power intake + substations (TNB), water, sewerage, telecom ducting, fire systems, standby power, solar provision
WP04 | Roads, drainage, landscape | Internal heavy-duty pavements, stormwater + flood mitigation, fencing, buffers
WP05 | Rail siding & trackworks | Sidings to KTMB corridor (subject to agreement), turnouts, terminal pavement — no gauge break exists; passive future-gauge provision only
WP06 | Rail systems & signalling | Terminal signalling, main-line interlocking interface, rail weighbridge-in-motion
WP07 | Container yard & intermodal | Paved yard, reefer racks, handling equipment, yard lighting/CCTV masts
WP08 | General & bonded warehousing | Ambient + bonded zones with customs-compliant segregation, docks, VAS areas
WP09 | Cold chain facilities | Multi-temperature rooms, blast freezing, insulated docks, halal-compliant segregation
WP10 | Truck terminal & inspection | Marshalling yards, queue lanes, weighbridges, driver amenities, inspection canopies

## Slide 30
Padang Besar Cross-Border Logistics Platform · Project Development Package · Draft for discussion — not an offer or representation of rights
30
SECTION 5 · WORK PACKAGES
WP11–WP20: buildings, digital systems and readiness
PROPOSED
WP | Package | Scope highlights
WP11 | Customs & agency facilities | Office/inspection space offered to JKDM, MAQIS, Immigration; scanner foundations (scanners typically govt-procured — TBC)
WP12 | Admin & commercial buildings | HQ, tenant offices (forwarders, brokers, banks), canteen, surau, clinic, training
WP13 | Workshops & MRO | Container repair/washing, equipment workshops, reefer PTI stations
WP14 | Security infrastructure | Bonded-grade perimeter, access control, guardhouses, secondary inspection areas
WP15 | Terminal operating system | TOS + rail planning module, EDI with KTMB/lines/hauliers, gate integration
WP16 | WMS, billing & ERP | Ambient/bonded/cold WMS, billing engine, customer portal, customs-system interfaces (subject to JKDM availability)
WP17 | Site-wide digital infrastructure | Fibre, private wireless, data centre, IoT, ANPR, AI CCTV, command centre, digital twin, cyber stack
WP18 | Testing & operational readiness | Integrated testing, dry runs with hauliers/forwarders, customs rehearsal, hiring & SOPs
WP19 | Taking-over & defects | Certification, punch lists, as-builts, digital twin handover
WP20 | Future expansion provision | Safeguarded land/utility corridors for Phase 2+ — passive design provision only

## Slide 31
Padang Besar Cross-Border Logistics Platform · Project Development Package · Draft for discussion — not an offer or representation of rights
31
SECTION 5 · WORK PACKAGES
Packaging strategy: how the WPs go to market
RECOMMENDATION
Single EPC wrap preferred. A fixed-price, date-certain EPC head contract over WP01–WP14 (+WP17 build) is the lender-friendly route; nominated subcontracts for rail systems and digital where specialists differ.
Rail packages are schedule-critical. WP05–WP06 need KTMB technical approval and possession planning — engage before EPC pricing, and design the platform to open road-only if rail consent lags.
Split-out option: WP15–WP17 as a systems-integrator contract under Prospek's integration accountability, if the technology consortium differs from the civil EPC.
Long-lead items to order early: refrigeration plant (WP09), handling equipment (WP07), substation equipment (WP03), scanners/ANPR (WP17).
Local content is structural, not optional: CIDB registration, Bumiputera contractor programmes and Malaysian subcontracting shape the EPC consortium from day one. [R62, R63]
SEQUENCING LOGIC
WP01–04
enabling
WP05–10
core
WP11–14
buildings
WP15–17
digital
WP18–19
readiness
WP20
expansion

## Slide 32
Padang Besar Cross-Border Logistics Platform · Project Development Package · Draft for discussion — not an offer or representation of rights
32
06
Digitalisation Strategy
The most digitally advanced land-border logistics facility in ASEAN — where the data layer is a revenue line, not a cost line.
Five-layer architecture
Sixteen capability modules
Command centre & cyber
Phasing & digital revenue

## Slide 33
Padang Besar Cross-Border Logistics Platform · Project Development Package · Draft for discussion — not an offer or representation of rights
33
SECTION 6 · DIGITALISATION
Five-layer architecture: field sensors to revenue insight
PROPOSED
L5 · INSIGHT & REVENUE
Integrated dashboard · digital twin analytics · data products · ESG reporting
L4 · APPLICATIONS
TOS · WMS · truck management/VBS · asset management (EAM) · billing · customer portal
L3 · PLATFORM
Digital twin core (GIS + BIM) · IoT platform · video analytics · data lake · API/EDI bus
L2 · NETWORK
Fibre backbone · private 4G/5G · LoRaWAN · redundant WAN · edge compute
L1 · FIELD
AI CCTV · ANPR · IoT sensors · drones · weighbridges · RFID/OCR gates · smart meters · access control
Open standards at every layer — no vendor lock-in; Chinese, Malaysian and international vendors compete at subsystem level.

## Slide 34
Padang Besar Cross-Border Logistics Platform · Project Development Package · Draft for discussion — not an offer or representation of rights
34
SECTION 6 · DIGITALISATION
Capability modules (1 of 2): the built environment goes digital
PROPOSED
Digital Twin
Live 3D model fusing GIS + BIM + IoT: design coordination → operations simulation → asset lifecycle
GIS
Land parcels, utilities, flood modelling, corridor and expansion planning
BIM
Level 2+ mandated across design (CIDB-aligned); CDE from day one; BIM-to-FM handover
Drones
Construction photogrammetry, volumetrics; then perimeter patrol and stack audits (CAAM permits)
IoT
Reefer telemetry, cold rooms, energy submetering, pavement/structure and flood sensors
AI CCTV
Safety (PPE, intrusion), security (perimeter), operations (dock occupancy, queue estimation)
ANPR
Malaysian + Thai plates at all gates; links truck identity to bookings and customs status
Predictive maintenance
Telematics + EAM condition-based maintenance for equipment, refrigeration, substations

## Slide 35
Padang Besar Cross-Border Logistics Platform · Project Development Package · Draft for discussion — not an offer or representation of rights
35
SECTION 6 · DIGITALISATION
Capability modules (2 of 2): operations, flow and trust
PROPOSED
Command Centre (ICC)
One control room: CCTV walls, TOS/WMS status, gates, border queue dashboard, incident management; hosts agency liaison desks
Warehouse automation
Phased: WMS-directed → RFID/barcode → conveyor/sortation and AMRs in e-commerce zones
Truck management (TMS/VBS)
Slot booking, driver app (BM/Thai/EN/CN), e-call-up, release tied to customs status
Smart parking
Occupancy sensing for marshalling + staff parking; dynamic signage; paid overnight parking
Traffic analytics
Queue length, dwell, lane throughput — shareable with police/JKR/customs
Asset management (EAM)
ISO 55000 register, lifecycle costing — underpins the long-term asset management services role
Integrated dashboard
Board/agency KPI layer: TEU, dwell, revenue, energy, safety, ESG — investor-grade reporting
Cybersecurity
IEC 62443 (OT) + ISO 27001 (IT), segmented customs-facing systems, SOC, Cyber Security Act 2024 compliance, PDPA

## Slide 36
Padang Besar Cross-Border Logistics Platform · Project Development Package · Draft for discussion — not an offer or representation of rights
36
SECTION 6 · DIGITALISATION
Phasing and the digital revenue logic
PROPOSED
Phase A · with EPC
CDE/BIM, GIS, drone capture, fibre, construction CCTV
Phase B · pre-ops
TOS, WMS, ANPR gates, VBS, ICC, cyber baseline
Phase C · maturity
predictive maintenance, AI analytics, twin simulation, data products
Phase D · expansion
warehouse automation, cross-border data corridors (subject to customs cooperation)
Digital as a revenue line (categories only — quantification pending feasibility, Section 10)
VBS fees
per-booking charges on truck slots
Data subscriptions
border-flow analytics for shippers & forwarders
Monitoring services
reefer/cold-chain monitoring-as-a-service
Portal & EDI fees
per-transaction charges
ICC services
monitoring/security sold to zone tenants
Principle: every digital system must either cut border dwell time or create a recurring income line — ideally both.

## Slide 37
Padang Besar Cross-Border Logistics Platform · Project Development Package · Draft for discussion — not an offer or representation of rights
37
07
Prospek Cerah Business Model
Not a broker: a developer with capital at risk, contracted deliverables and income that arrives only if the project is built and operates well.
Why not a broker
Eight roles
Lifecycle fit
Governance position

## Slide 38
Padang Besar Cross-Border Logistics Platform · Project Development Package · Draft for discussion — not an offer or representation of rights
38
SECTION 7 · PROSPEK CERAH
Why Prospek Cerah is not a broker
PROPOSED
Dimension | Broker | Prospek Cerah (proposed)
Time horizon | Transaction close | Full lifecycle: development → operations → expansion
Accountability | None after introduction | Contracted deliverables: milestones, PMO KPIs, digital SLAs
Capital | No skin in the game | Development capital at risk pre-financial-close; proposed SPV equity
Value creation | Access | Project definition, structuring, integration, delivery capability
Revenue | One-off commission | Milestone-earned fees + long-term recurring income
Relationships | Introduces, then exits | Holds and manages stakeholder relationships permanently
The economic point for partners: the majority of Prospek's proposed income arrives only if the project is built and operates well.

## Slide 39
Padang Besar Cross-Border Logistics Platform · Project Development Package · Draft for discussion — not an offer or representation of rights
39
SECTION 7 · PROSPEK CERAH
Eight roles across the project lifecycle
PROPOSED
1 · Project Developer
Originates and defines the project; funds pre-development; carries risk to financial close
2 · Consortium Builder
Assembles SPV shareholders, EPC, technology, operator, financiers as one integrated package
3 · Business Development
Builds the cargo book: shipper pre-commitments, anchor tenants, Thai counterparts
4 · PMO
Owner's-side programme management across WP01–WP20: schedule, cost, risk, lender reporting
5 · Technology Integrator
Accountable for WP15–WP17 systems working together and with government systems
6 · Digitalisation Partner
Long-term operator of the digital layer under SLA — recurring service income
7 · Asset Management
ISO 55000 management of the asset across its life; handback compliance if concession applies
8 · Strategic Partner
Standing counterpart to owner, state, federal and Shandong for expansion and replication
Develop (Yr 0–2): roles 1–3 · Deliver (Yr 2–5): roles 4–5 · Operate (Yr 5+): roles 6–8. Governance: SPV shareholder + contracted PMO + digital/AM services — all related-party contracts disclosed and market-benchmarked.

## Slide 40
Padang Besar Cross-Border Logistics Platform · Project Development Package · Draft for discussion — not an offer or representation of rights
40
08
Shandong Hi-Speed Role
What SDHS could undertake — structured for negotiation. No commitment by SDHS exists; corporate facts are referenced.
Verified profile
Strategic fit
Scope options
Commercial postures

## Slide 41
Padang Besar Cross-Border Logistics Platform · Project Development Package · Draft for discussion — not an offer or representation of rights
41
SECTION 8 · SHANDONG HI-SPEED
Verified profile: scale, rail logistics and live Malaysia activity
PUBLICLY VERIFIED
>9,000 km
expressways operated — provincial SOE, HQ Jinan [R66, R68]
RMB 1.76tn
reported total assets; Fortune Global 500 #401 (company-published — cross-check in DD) [R67]
Qilu Express
China–Europe freight brand; 2,500 Shandong-handled trips in 2023 [R69]
RMB ~70bn
revenue of listed EPC arm Shandong Hi-Speed Road & Bridge (000498.SZ) [R70]
Live in Malaysia: framework agreement with Bursa-listed PTT Synergy (23 Sep 2025) for smart/automated warehousing — reported ~RM2bn (Malaysian media) vs RM6bn/2M pallet positions (Chinese trade press); discrepancy disclosed. [R72, R73]
China Shandong International (CSI), wholly-owned since 2008, has a Malaysian-registered entity. [R71]
Ratings: Moody's first-time A3 (2018; current parent rating not publicly confirmable); Fitch A－/Stable on HK-listed Shandong Hi-Speed Holdings. [R74]
No published SDHS commitment to Perlis or Padang Besar exists — the role described in this section is proposal-stage only.

## Slide 42
Padang Besar Cross-Border Logistics Platform · Project Development Package · Draft for discussion — not an offer or representation of rights
42
SECTION 8 · SHANDONG HI-SPEED
Scope SDHS could undertake — and three commercial postures
PROPOSED
Domain | Potential SDHS scope | WPs
Civil & infrastructure | Earthworks, roads, pavements, rail sidings & systems (with KTMB approval), utilities | WP02–07, 10
Warehousing & buildings | Ambient/bonded/cold warehouses; customs, admin, commercial buildings; workshops | WP08–09, 11–13
Digital & ICT | Site-wide digital infrastructure delivery; fibre, data centre — under Prospek integration | WP15–17
Operations & maintenance | Terminal O&M participation via logistics arms; long-term infrastructure maintenance | Ops phase
Future expansion | EPC for Phase 2+; potential co-investment in expansion capex | WP20
Posture 1
EPC contractor only — date-certain, price-certain wrap; simplest entry
Posture 2
EPC + SPV equity — aligns delivery and ownership; needs related-party safeguards
Posture 3
EPC + equity + O&M — deepest integration; shares operating risk and upside
SDHS internal-approval needs: verified land/rights, bankable feasibility, tenure clarity, governance framework, CIDB licensing and Chinese outbound approvals (NDRC/MOFCOM/SAFE).

## Slide 43
Padang Besar Cross-Border Logistics Platform · Project Development Package · Draft for discussion — not an offer or representation of rights
43
09
Investment Model
Investor universe, revenue streams, capital and equity structure, PPP options, risk allocation, funding stages and exits — structures only, no invented numbers.
Investor universe
Revenue streams
Capital & PPP structure
Risk allocation & exits

## Slide 44
Padang Besar Cross-Border Logistics Platform · Project Development Package · Draft for discussion — not an offer or representation of rights
44
SECTION 9 · INVESTMENT MODEL
The investor universe — and what each needs to see
PROPOSED
Investor category | Examples of type | What they need to see
Strategic — construction/infra | Shandong Hi-Speed Group and peers | EPC pipeline + equity upside; government endorsement
Strategic — logistics operators | Terminal operators, rail logistics groups, 3PLs | Operating control or strong agreements; cargo commitments
Logistics real estate platforms | Regional industrial developers & funds (e.g., LOGOS-type JVs) [R81] | Leasable product, tenant covenants, yield profile
Financial — infrastructure funds | ASEAN/Asia infra and PE funds | Contracted revenue share, credible exit, governance rights
Malaysian institutions | GLIC/pension-type investors (mandate-dependent) | National-interest alignment, stable yield, local partner quality
DFIs / policy lenders | IFC, AIIB, ECAs, policy banks — Thanaleng precedent [R75, R76] | ESG compliance, trade-facilitation impact, sovereign context
State/federal vehicles | State economic corporations, facilitation funds | Jobs, state revenue, border modernisation outcomes

## Slide 45
Padang Besar Cross-Border Logistics Platform · Project Development Package · Draft for discussion — not an offer or representation of rights
45
SECTION 9 · INVESTMENT MODEL
Revenue architecture: six stream families
PROPOSED
CORE TERMINAL
Rail handling · container lift/storage · transshipment · reefer plugs · empty depot
WAREHOUSING
Ambient/bonded/cold leasing · VAS (kitting, labelling) · e-fulfilment
BORDER SERVICES
Truck marshalling/slot fees · weighbridge · inspection support · paid parking
COMMERCIAL
Office/retail rents · fuel & service concessions · advertising
DIGITAL
VBS fees · data products · reefer monitoring · portal transaction fees
DEVELOPMENT & MGMT
PMO fees · asset management fees · expansion development fees (accrue to service providers, not SPV)
No stream is quantified in this package: each enters the lender base case only with an identified contractual or statistical basis (Section 10).

## Slide 46
Padang Besar Cross-Border Logistics Platform · Project Development Package · Draft for discussion — not an offer or representation of rights
46
SECTION 9 · INVESTMENT MODEL
Capital structure logic and PPP model options
PROPOSED
CAPITAL STACK (logic, no figures)
Senior debt
Project finance sized on contracted revenue — BPMB precedent at PIP; AIIB–Malaysian bank platforms; ECA cover; sukuk-capable [R25, R80]
Mezzanine
Optional gap layer from strategic sponsors
Sponsor equity
Consortium equity, staged against milestones
Govt support
To be explored, never assumed: tenure, incentives (MIDA/zone), facilitation funding [G]
PPP MODEL OPTIONS (depends entirely on true land position)
Model | When it fits
Private land, build-own-operate | Land privately held; licensed private facility
State land lease + BOT/BOO | State land; requires state agreement
Concession incl. agency facilities | Government wants integrated border facilities (WP11)
Hybrid landlord model | SPV as landlord; specialist operators as tenants — reduces operating risk
PIKAS 2030 preference: competitive RFP and user-pays projects — engagement route via UKAS if any government facility/concession element applies. [R61]

## Slide 47
Padang Besar Cross-Border Logistics Platform · Project Development Package · Draft for discussion — not an offer or representation of rights
47
SECTION 9 · INVESTMENT MODEL
Risk allocation, funding stages and exit options
PROPOSED
Risk | Allocated to | Instrument
Construction | EPC contractor | Fixed-price date-certain wrap, LDs, performance security
Cargo / market | Shared | Anchor pre-commitments + sponsor equity buffer
Operating performance | Operator | KPI-linked O&M contract with step-in rights
Border policy / customs | Not transferable | Government engagement; diversified revenue mix
Land / approvals | Development phase | Precondition to financial close — never carried by lenders
1 · Development capital
sponsors, highest risk
2 · Financial close
equity + debt committed
3 · Construction
milestone drawdowns
4 · Operations ramp
working capital
5 · Expansion
retained cash / new partners
EXIT OPTIONS
Trade sale to strategic operator or logistics RE platform
Infra fund sale once cash flows season
REIT injection of stabilised warehouse assets
IPO of the platform company at scale
Refinancing for partial sponsor liquidity

## Slide 48
Padang Besar Cross-Border Logistics Platform · Project Development Package · Draft for discussion — not an offer or representation of rights
48
10
Financial Model Framework
Deliberately no invented numbers. The model structure and every assumption class that must be evidenced before a single figure is entered.
Modelling principles
Revenue categories
Cost categories & sensitivities
Outputs per audience

## Slide 49
Padang Besar Cross-Border Logistics Platform · Project Development Package · Draft for discussion — not an offer or representation of rights
49
SECTION 10 · FINANCIAL FRAMEWORK
Modelling principles and revenue categories (no figures)
PROPOSED
Every input traces to evidence · three cases minimum (base/downside/upside) · MYR model with THB/USD/CNY sensitivity · no revenue in the lender case without a contractual or statistical basis
Category | Potential lines (to be quantified only after evidence)
Terminal & rail | Rail handling per TEU · storage & empty depot · reefer plugs · wagon/shunting services (KTMB commercial terms pending)
Warehousing & property | Ambient rents · bonded premiums · cold chamber/pallet/blast-freeze · built-to-suit returns · sub-lease income (tenure permitting)
Border & vehicle services | Marshalling slots · secure parking · weighbridge · driver amenities & concessions
Operating income | Handling labour, VAS · customs brokerage facilitation (licensing pending) · equipment rental
Recurring income | Multi-year leases & anchor tenancies · third-party O&M · utility resale margins (regulatory check required)
Digital / PMO / AM / concession | VBS & data subscriptions · portal fees · PMO & development fees · asset management fees · concession/availability income if structure eventuates (pending)

## Slide 50
Padang Besar Cross-Border Logistics Platform · Project Development Package · Draft for discussion — not an offer or representation of rights
50
SECTION 10 · FINANCIAL FRAMEWORK
Cost classes, sensitivities and outputs per audience
PROPOSED
COST CLASSES (priced, not guessed)
EPC capex per WP — from contractor pricing, not benchmarks alone
Land cost/lease — from confirmed tenure terms (pending)
Equipment capex and renewal cycles
Energy (largest cold-chain driver), labour, maintenance, insurance
Digital opex: licences, SOC, connectivity, refresh cycles
Concession fees/royalties if applicable (pending)
KEY SENSITIVITIES
Throughput growth vs verified baselines · ramp-up length · anchor pre-commitment share
Cross-border rail interchange capture (KTMB–SRT service patterns) · energy tariffs · MYR/THB
Audience | Model outputs required
Banks | DSCR profile, gearing, tenor/tail, security coverage
Investors | Equity IRR, payback, dividend profile, exit valuation logic
Government | Jobs, state revenue, trade-facilitation KPIs, fiscal cost of support
Board | Funding plan, milestone cash needs, downside survivability

## Slide 51
Padang Besar Cross-Border Logistics Platform · Project Development Package · Draft for discussion — not an offer or representation of rights
51
11
Due Diligence Checklist
Eleven workstreams. Every item answered with documents, not statements — the evidence set for investment committees and bank credit processes.
Corporate · Land · Project
Government · Technical
Financial · Legal · Commercial
ESG · Operational · Digital

## Slide 52
Padang Besar Cross-Border Logistics Platform · Project Development Package · Draft for discussion — not an offer or representation of rights
52
SECTION 11 · DUE DILIGENCE
Workstreams A–E: the existential checks
RECOMMENDATION
Workstream | Key items (abridged — full checklist in package document)
A · Corporate | SSM extracts, UBOs, board authorisations, audited accounts, charges & litigation searches, all existing MOUs/agreements with status
B · Land | Titles per parcel (owner, category, conditions) · state/reserve/Malay Reserve status · encumbrances & caveats · zoning · KTMB/Railway Assets Corporation land involvement · flood history
C · Project | Existing studies & master plans · what exists today vs aspiration · prior tenders/liabilities · utilities availability · interface with PIP and legacy terminal operators
D · Government | Written state support · federal engagement status (MOT, MITI, JKDM, UKAS) · NCIA status · KTMB engagement · issued gazettes/licences · Thai-side engagement
E · Technical | Geotech adequacy · rail connection feasibility (gradient, possessions) · road capacity · utility loads (cold-chain power) · flood modelling · EIA screening
Workstream B (Land) is the gating item: nothing proceeds without title verification.

## Slide 53
Padang Besar Cross-Border Logistics Platform · Project Development Package · Draft for discussion — not an offer or representation of rights
53
SECTION 11 · DUE DILIGENCE
Workstreams F–K: bankability and operability
RECOMMENDATION
Workstream | Key items (abridged)
F · Financial | Owner funding capacity · existing financing/liens · tax structure & incentive eligibility · basis of any previously circulated figures (validate or discard)
G · Legal | Rights held vs rights claimed (evidence per item) · foreign investment limits · licensing map (bonded, forwarding, CIDB, CAAM) · sanctions screening of all counterparties
H · Commercial | Verified cargo baseline (KTMB/Customs data requests) · named anchor prospects & commitment status · competing facilities pipeline · tariff benchmarks · demand interviews
I · Environmental & Social | EIA determination · site occupants/displacement · heritage · IFC Performance Standards / Equator alignment · climate resilience
J · Operational | Operating model & candidate operators · labour availability in Perlis · border hours as throughput cap · bonded security requirements
K · Digital | Existing systems · fibre/carrier availability · JKDM interface constraints · PDPA & Cyber Security Act 2024 obligations · vendor landscape

## Slide 54
Padang Besar Cross-Border Logistics Platform · Project Development Package · Draft for discussion — not an offer or representation of rights
54
12
Questions for the Project Owner
Collaborative, professional questions that help the owner assemble what investors, Shandong, technology partners and banks will ask for anyway.
Foundation & land
Government & commercial
Structure & finances
Timeline & process

## Slide 55
Padang Besar Cross-Border Logistics Platform · Project Development Package · Draft for discussion — not an offer or representation of rights
55
SECTION 12 · OWNER QUESTIONS
Twenty-six questions in seven groups (selection)
RECOMMENDATION
FOUNDATION
How did the project originate and what exists today? What does success look like in 5 and 15 years?
LAND & RIGHTS
Which parcels, what tenure, any existing agreements? Does any element rely on railway reserve or KTMB land?
GOVERNMENT
Who has been engaged, and is there anything in writing? Any JKDM discussions on bonded/zone status? KTMB response on sidings?
COMMERCIAL
Which cargo flows anchor demand, and on what evidence? How is the platform positioned vs Perlis Inland Port — integration, complement, or competition?
STRUCTURE
What role does the owner wish to retain? What are expectations on ownership and control? Any commitments a consortium must respect?
FINANCES
What has been invested to date and by whom? Expected owner/partner/bank funding split? Any liabilities attached to land or project?
PROCESS
What timeline and external deadlines apply? Openness to structured DD under NDA with a data room? Who is authorised to negotiate?
Tone: these questions accelerate the owner's own fundraising — they are the same list any serious counterpart will bring.

## Slide 56
Padang Besar Cross-Border Logistics Platform · Project Development Package · Draft for discussion — not an offer or representation of rights
56
13
Consortium Structure
A single-purpose Malaysian SPV with clean contracts around it — designed to satisfy the ≥51% Malaysian ownership floor and lender governance standards.
SPV structure
Roles & candidates
Agreements map
Governance principles

## Slide 57
Padang Besar Cross-Border Logistics Platform · Project Development Package · Draft for discussion — not an offer or representation of rights
57
SECTION 13 · CONSORTIUM
Proposed SPV structure (percentages deliberately unstated)
PROPOSED
GOVERNMENT (State / Federal)
tenure · approvals · incentives · possible state equity
PROJECT SPV (Malaysia)
single-purpose company · owns & finances the platform · ≥51% Malaysian [R62]
SPONSOR EQUITY
Prospek Cerah · Shandong Hi-Speed (optional) · local partner(s) · project owner (land) · financial investors
LENDERS
Malaysian/regional banks · BPMB · ECAs · DFIs (IFC/AIIB precedent at Thanaleng) — security over SPV
EPC Contract
SDHS-led + mandatory local participation
Technology
Prospek-integrated vendor consortium
Operator(s)
Terminal & warehouse O&M, KPI-linked
PMO / Dev Mgmt
Prospek, with lender's engineer oversight
The SPV contracts everything outward; related-party contracts (Prospek services, SDHS EPC) disclosed, benchmarked and approved by non-conflicted directors.

## Slide 58
Padang Besar Cross-Border Logistics Platform · Project Development Package · Draft for discussion — not an offer or representation of rights
58
SECTION 13 · CONSORTIUM
Nine key agreements and four governance principles
PROPOSED
# | Agreement
1 | Shareholders' Agreement — governance, reserved matters, transfers, deadlock
2 | Land lease / SPA / land-for-equity — form follows verified tenure
3 | Concession / development agreement with state (if applicable)
4 | EPC Contract (FIDIC Silver/Yellow basis for lender-financed EPC)
5 | O&M / Terminal Operating Agreement(s)
6 | Technology supply, integration and SLA agreements
7 | Development Management / PMO Agreement
8 | Financing documents — facility, security, lender direct agreements
9 | Anchor customer / tenancy pre-commitments
GOVERNANCE PRINCIPLES
Board proportional to equity, with protective minority rights
Related-party contracts disclosed, market-benchmarked, approved by non-conflicted directors — essential for lenders and co-investors
Independent lender's engineer and model auditor at financial close
ESG and compliance committee from day one — a border/customs environment demands clean governance (the PKFZ lesson) [R79]

## Slide 59
Padang Besar Cross-Border Logistics Platform · Project Development Package · Draft for discussion — not an offer or representation of rights
59
14
Risk Register
Twenty-five risks across ten categories, qualitatively scored pre-feasibility. Five are gating: they must be addressed before money moves.
Gating risks
Full register by category
Mitigation ownership

## Slide 60
Padang Besar Cross-Border Logistics Platform · Project Development Package · Draft for discussion — not an offer or representation of rights
60
SECTION 14 · RISK REGISTER
Five gating risks — address before money
RECOMMENDATION
R01 · Land & rights
Position weaker than represented; project premise fails
Land DD as Phase 1 gate; zero capital before title verification
R02 · Government support
Not secured, or shifts with political cycles
Written instruments early; multi-party alignment (state + NCIA + federal)
R06 · Demand evidence
Cargo volumes below case; slow ramp
Anchor pre-commitments before financial close; conservative lender case
R09 · Financeability
Greenfield border asset fails to raise acceptable debt
ECA/DFI tracks in parallel; staged capex; strong sponsor equity signal
R15 · Rail connection
KTMB siding approval/possession delays
Early technical agreement; design to operate road-only in interim
Column 3 = mitigation. Ratings are qualitative team judgments at pre-feasibility stage — to be re-scored quantitatively in due diligence.

## Slide 61
Padang Besar Cross-Border Logistics Platform · Project Development Package · Draft for discussion — not an offer or representation of rights
61
SECTION 14 · RISK REGISTER
Register overview: 25 risks across ten categories
RECOMMENDATION
Category | Representative risks (L/I at pre-feasibility) | Core mitigations
Government & border | Licences delayed (M/H) · border policy shifts (M/H) · Thai-side lag (M/M) | Early JKDM engagement; design to operate without zone status initially; bilateral corridor dialogues
Commercial | Competition from PIP/BKH/Thai facilities (M/M) · anchor concentration (M/M) · KTMB haulage economics (M/M) | Complement/integrate positioning; tenant diversification; early KTMB commercial MOU
Financial | FX (M/M) · energy escalation vs cold chain (M/M) | Natural hedging; tariff pass-through; solar PV
Construction & technical | Ground/flood conditions (M/M) · EPC overrun (M/H) · interfaces (M/M) · utility capacity (M/M) | Full GI before pricing; fixed-price wrap; single-wrap preference; early TNB application
Technology & operations | Integration failure (M/M) · cyber breach (M/H) · operator underperformance (L/M) · labour gap (M/M) | Open standards + escrow; IEC 62443/ISO 27001 + SOC; KPI O&M with step-in; NCIA training programmes
Political & ESG | Geopolitics (L/M) · sanctions exposure (L/H) · EIA conditions (M/M) · DFI ESG bar (L/H) | Balanced consortium; DD screening + substitution rights; IFC PS-aligned ESMS from Phase 1

## Slide 62
Padang Besar Cross-Border Logistics Platform · Project Development Package · Draft for discussion — not an offer or representation of rights
62
15
Roadmap
Seven phases, five governance gates. Indicative durations only — the critical path runs through land verification and government process.
Phase plan
Governance gates
First 90 days

## Slide 63
Padang Besar Cross-Border Logistics Platform · Project Development Package · Draft for discussion — not an offer or representation of rights
63
SECTION 15 · ROADMAP
Seven phases from due diligence to operations
PROPOSED
1 · Due Diligence
3–6 mo · land & rights gate, red-flag report
2 · Consortium
3–6 mo · heads of terms, feasibility, partners
3 · Investment
6–12 mo · SPV, land agreements, financial close
4 · Engineering
9–12 mo · EIA, FEED in BIM, EPC tender
5 · Construction
24–36 mo · phased, early-revenue sequencing
6 · Digitalisation
runs phases 4–7 · ICC live at opening day
7 · Operations & growth
ramp-up, ISO 55000 regime, refinancing, Phase 2 triggers
Phases 1–2 overlap deliberately: consortium conversations begin during due diligence, but no party commits capital until Gate G1 clears.

## Slide 64
Padang Besar Cross-Border Logistics Platform · Project Development Package · Draft for discussion — not an offer or representation of rights
64
SECTION 15 · ROADMAP
Five governance gates — and the first 90 days
RECOMMENDATION
Gate | Decision | Evidence required
G1 | Proceed past DD | Clean land/rights, government support signals, demand baseline
G2 | Sign consortium | Positive feasibility, aligned partners, heads of terms with owner
G3 | Financial close | Bankable package: contracts, approvals, committed funding
G4 | Notice to proceed | EPC signed, land access, insurance, CPs met
G5 | Open for operations | Commissioning complete, licences in force, operator ready
FIRST 90 DAYS
Execute NDA + information request (Section 11 list) with project owner
Land title searches and encumbrance checks
Owner workshop on the 26 questions (Section 12)
Soundings: state government, NCIA, KTMB, JKDM
Brief Shandong Hi-Speed on posture options (Section 8)
Commission cargo demand scan and PIP positioning study
Output: Red Flag Report → G1 go/no-go

## Slide 65
Padang Besar Cross-Border Logistics Platform · Project Development Package · Draft for discussion — not an offer or representation of rights
65
A
Appendix
Visual asset recommendations · assumptions register · consolidated references.
Photo & map plan
Assumptions A01–A24
References R1–R82

## Slide 66
Padang Besar Cross-Border Logistics Platform · Project Development Package · Draft for discussion — not an offer or representation of rights
66
APPENDIX
Visual asset plan: photos, maps and icons for the final deck
RECOMMENDATION
Asset | Recommendation | Source / rights note
Hero photo | Padang Besar station rail yard with freight wagons at dawn; alternative: ASEAN Express launch imagery | Commission photographer on site visit; Bernama/KTMB imagery requires licence
Border imagery | ICQS complex approach, truck queue (illustrates the marshalling case) | Site visit photography; avoid security-sensitive angles — clear with ICQS authorities
PIP context | Perlis Inland Port gate/yard (establishes the incumbent honestly) | Mutiara Perlis/NCIA press assets with permission
Corridor map | Peninsular map: Padang Besar–Penang–Klang rail spine + Hat Yai–Bangkok–Laos–China; inset: border-town detail | Redraw from OpenStreetMap (ODbL attribution) — do not screenshot Google Maps
Site plan | Only after owner confirms parcels — placeholder schematic until then | Owner survey data; licensed surveyor output
Icons | Single-line style (rail, truck, warehouse, snowflake, shield, satellite) — one family throughout | Licensed icon set (e.g., Streamline/Noun Project licence)
Drone footage | Construction-phase progress films for investor updates (Phase 5) | CAAM permit required near border zone — check restricted airspace

## Slide 67
Padang Besar Cross-Border Logistics Platform · Project Development Package · Draft for discussion — not an offer or representation of rights
67
APPENDIX
Assumptions register (1 of 2): A01–A12
PENDING OWNER CONFIRMATION
# | Assumption | Class
A01 | A defined project exists with an owner able to grant land/rights | Owner
A02 | Sufficient land near border/rail can be secured on lender-acceptable tenure | Owner
A03 | Project can position as complement/integrator to Perlis Inland Port | Owner/Market
A04 | KTMB will agree to siding connection and commercial services | Government
A05 | Customs/bonded/FCZ licensing obtainable for the site | Government
A06 | Border cargo demand keeps growing in line with verified trends | Market
A07 | Cold-chain white space exists at the border | Judgment/Market
A08 | Truck marshalling services are monetisable against border hours | Judgment/Market
A09 | Shandong Hi-Speed would consider EPC and/or equity roles | Owner
A10 | Prospek Cerah can evidence capability for its eight roles | Owner
A11 | Consortium can satisfy 51% Malaysian floor + Bumiputera conditions | Government
A12 | Project financing achievable given BPMB/IFC/AIIB precedents | Market

## Slide 68
Padang Besar Cross-Border Logistics Platform · Project Development Package · Draft for discussion — not an offer or representation of rights
68
APPENDIX
Assumptions register (2 of 2): A13–A24
PENDING OWNER CONFIRMATION
# | Assumption | Class
A13 | The 20-WP breakdown matches final master plan scope | Judgment
A14 | Digital systems can interface with JKDM systems at reasonable cost | Government
A15 | Indicative phase durations achievable if gating items clear | Judgment
A16 | State support for additional logistics investment is obtainable | Government
A17 | Border Economic Zone will produce usable incentives | Government
A18 | SRT Hat Yai–Padang Besar double-tracking proceeds on reported timeline | Government/Market
A19 | Qualitative risk ratings reflect the true pre-feasibility profile | Judgment
A20 | No adverse existing agreements encumber the project or site | Owner
A21 | Thai counterparts cooperate on corridor improvements | Government
A22 | Published PIP figures are broadly accurate despite source conflicts | Judgment
A23 | Financial model structure covers all material categories | Judgment
A24 | Consortium roles map is negotiable to signature without structural change | Judgment

## Slide 69
Padang Besar Cross-Border Logistics Platform · Project Development Package · Draft for discussion — not an offer or representation of rights
69
APPENDIX
References (1 of 2): border, rail, PIP, trade
PUBLICLY VERIFIED
R1–R5 Border town, station, juxtaposed controls, operating hours — Wikivoyage; Border Crossing Hub; Wikipedia (Padang Besar railway station); FMT (2017); Mekong Region guide
R6–R8 Roads — Wikipedia FT7/FT79; paultan.org (BKH–Sadao road, 10 Jul 2026)
R9–R13 Rail & services — China Daily (gauge); KTMB Kargo; The Star (block train 2022; ASEAN Express 2024); railmarket.com (STC, Dec 2025)
R14–R28 Perlis Inland Port — The Edge; The Star (25 Mar 2025); Railway Gazette (13 Apr 2025); Bernama (30 May 2026); BPMB; NCER; MIDA; FMT (14 Jul 2026); Harakah Daily; RMCD; WCO News; CAREC; Citaglobal reports
R29–R41 Rail policy & PIP ecosystem — KTMB ETS; Nation Thailand (Thanaleng gauge, SRT double-tracking); FMT; SCMP; Malay Mail (13MP rail); ANN; NST (Kalmar); The Edge (GDC, Maritime Corridor); MIDA (MOU/MOC); Business Today (Berjaya)
R42–R51 Border & trade — Thai PRD; Malaysiakini; Singapore Customs (ASW); ACTS portal; MITI (JTC US$30bn); Nation Thailand (trade 2024/2025, checkpoint values); Thairath; KLSE Screener; The Star (Penang 70%)
Full citation list with URLs: docs/17_references.md in the package repository.

## Slide 70
Padang Besar Cross-Border Logistics Platform · Project Development Package · Draft for discussion — not an offer or representation of rights
70
APPENDIX
References (2 of 2): policy, Perlis, Shandong, benchmarks
PUBLICLY VERIFIED
R52–R55 ASEAN & corridors — ASEAN Connectivity Strategic Plan 2026–2035; ADB (IMT-GT); Wikipedia (Kunming–Singapore); Bangkok Post (Land Bridge)
R56–R63 Federal & rules — NCER/NCIA; MIDA (CVIA); PMO (NTP 2019–2030); MOT (LTFM); Malay Mail (Border Economic Zone; 51% ports rule); UKAS/The Star (PIKAS 2030); MITI (equity conditions)
R64–R65 Perlis state — Malay Mail (2026 budget); Perlis state portal (growth areas)
R66–R74 Shandong Hi-Speed — Wikipedia; Baidu Baike (flagged company-published); Devex; Xinhua Silk Road (Qilu); Alpha Spread (000498.SZ); CSI/CTOS record; The Star & The Edge (PTT Synergy, Sep 2025); Moody's (2018 A3)
R75–R82 Benchmarks & financing — IFC & AIIB (Thanaleng); UNESCAP (Lat Krabang, Malaysian dry ports); ResearchGate; The Edge (PKFZ); AIIB (US$6bn Malaysian bank partnership); Sime Darby Property/Mingtiandi (LOGOS fund)
Citation-quality note: aggregator and trade-press items are flagged in text and must be replaced with primary documents (Bursa filings, gazettes, audited statements) during due diligence.

## Slide 71
Padang Besar Cross-Border Logistics Platform · Project Development Package · Draft for discussion — not an offer or representation of rights
71
NEXT STEP
One meeting with the project owner
unlocks everything else.
The corridor thesis is verified; the project's rights are not — Phase 1 due diligence resolves that in 3–6 months at development-capital cost only
The 26 owner questions and 11 due-diligence workstreams in this package are the agenda for that meeting
No capital, no commitments and no representations until Gate G1 clears
This document contains no representation of ownership, concession, operating rights or licences. All items not publicly verified are pending confirmation from the project owner.